## Information
ATM Network and Card Payment System
Group no. | 2
Division | B
PRN | Name
25030241063 | Aviral Bajpei
25030241070 | Garvit Saraswat
25030241074 | Karthik MD
25030241075 | Kirat Kaur Bhatia
25030241076 | Kunal Chakraborty
25030241077 | M Abhishek
25030241078 | Madhur Gupta

## Likelihood consequence risk
LIKELIHOOD RATING |  |  | IMPACT RATING |  |  |  |  | RISK RATING
Consequence
Probability of Occurrence |  | Description | Potential Impact |  | Financial | People | Reputation | Likelihood | Insignificant | Minor | Moderate | Major | Severe
[9 empty] | 1 | 2 | 3 | 4 | 5
Almost certain | 5 | (1) Motivation of Threat Source: Extremely High – financially/criminally driven, persistant incentive. (2) Capability of Threat Source: Highly Capable - Well-resourced and highly skilled (Maybe organized groups with proven ability to bypass defenses). (3) Effectiveness of Controls: Absent or wholly ineffective – attack success is very likely. (4) Frequency of Occurance: Might occur frequently - Expected monthly or more often; multiple incidents across regions each year. | Severe | 5 | • Quantitative Expected Loss: Greater than ₹50 Cr, including large-scale fraud or settlement losses. • Operational Impact: Prolonged outage lasting more than 7 days, leading to systemic disruption. • Compliance: Heavy penalties or potential suspension of services by regulators. | • Customer Impact: Widespread harm, with thousands unable to access funds or suffering severe losses. • Employee Impact: Severe consequences such as mass accountability, disciplinary action, or morale collapse. | • Customer Trust: Long-term erosion of public confidence, highly difficult to rebuild. • Client/Partner Trust: Major withdrawal of business clients or partners due to loss of confidence. • Regulatory Standing: Severe intervention such as investigations, restrictions, or license suspensions. | 5 - Almost Certain | Low | Medium | High | Extreme | Extreme
Likely | 4 | (1) Motivation of Threat Source: High to Very High – strong incentive, sustained interest. (2) Capability of Threat Source: Capable to Highly Capable – has tools/skills readily available. (3) Effectiveness of Controls: Partially effective – may slow or detect, but often bypassed. (4) Frequency of Occurance: Might occur periodically - Expected once or a few times a year in a given environment. | Major | 4 | • Quantitative Expected Loss: Between ₹10–50 Cr from fraud, outages, or penalties. • Operational Impact: Multi-day outage (3–7 days) causing significant financial disruption. • Compliance: Significant penalties and mandated corrective actions from regulators. | • Customer Impact: Large number of customers unable to transact or facing financial distress. • Employee Impact: Significant stress, investigations, and reputational harm internally. | • Customer Trust: Sustained damage, requiring major effort to restore confidence. • Client/Partner Trust: Reduced confidence among partner institutions or merchants. • Regulatory Standing: Restrictions imposed, such as limits on new business activities. | 4 - Likely | Low | Medium | High | High | Extreme
Possible | 3 | (1) Motivation of Threat Source: Moderate to High – situational or opportunistic. (2) Capability of Threat Source: Moderate to Capable – enough tools/skills to succeed if conditions are favorable. (3) Effectiveness of Controls: Reasonably effective – impedes success, but some gaps exist. (4) Frequency of Occurance: Might Occur occasionally - Expected once every 1–3 years. | Moderate | 3 | • Quantitative Expected Loss: Between ₹1–10 Cr, with manageable but material consequences. • Operational Impact: Short outage of 1–2 days, creating regional or limited disruption. • Compliance: Moderate penalties such as fines or formal warnings. | • Customer Impact: Moderate number of customers affected, inconvenienced, or reimbursed. • Employee Impact: Limited issues such as isolated disciplinary action or performance reviews. | • Customer Trust: Noticeable erosion of trust among certain segments or regions. • Client/Partner Trust: Concerns raised by partners, requiring reassurance. • Regulatory Standing: Warning letters or heightened oversight. | 3 - Possible | Low | Low | Medium | High | High
Unlikely | 2 | (1) Motivation of Threat Source: Low to Moderate – limited or sporadic incentive. (2) Capability of Threat Source: Limited to Moderate – lacks full expertise, but may try basic exploits . (3) Effectiveness of Controls: Generally effective and reliable, though not foolproof – residual vulnerabilities could be exploited. (4) Frequency of Occurance: Might occur rarely - Expected once every 3–10 years. | Minor | 2 | • Quantitative Expected Loss: Between ₹50 Lakh–1 Cr, creating low-level financial strain. • Operational Impact: Limited outage lasting only hours, with localized impact. • Compliance: Small penalties or minor compliance issues flagged. | • Customer Impact: Few customers temporarily affected with quick recovery or reimbursement. • Employee Impact: Minimal internal consequences or workload increase. | • Customer Trust: Minor issues that do not materially damage confidence. • Client/Partner Trust: Temporary concerns, quickly resolved with communication. • Regulatory Standing: Notices issued without further consequences. | 2 - Unlikely | Low | Low | Medium | Medium | High
Rare | 1 | (1) Motivation of Threat Source: Negligible/Lack of to Low – no real incentive. (2) Capability of Threat Source: Insufficient – lacks tools, knowledge, or access. (3) Effectiveness of Controls: Very strong and layered – success is highly improbable. (4) Frequency of Occurance: Might occur extremely rarely or unprecedented - once in 10+ years, if ever. | Insignificant | 1 | • Quantitative Expected Loss: Less than ₹50 Lakh, with negligible financial significance. • Operational Impact: Negligible or no outage, with uninterrupted operations. • Compliance: No penalties or compliance concerns. | • Customer Impact: No meaningful harm; only minor inconvenience possible. • Employee Impact: Negligible impact on workload or morale. | • Customer Trust: No significant loss of trust or reputation. • Client/Partner Trust: No concerns raised by business partners or institutions. • Regulatory Standing: No involvement from regulators. | 1 - Rare | Low | Low | Low | Medium | Medium

## Risk Assessment & Treatment
| Asset Name | ATM Network and Card Payment System
# | Threat | Vulnerablity | CIA impact | Risk Likelihood | Risk Impact | Overall Risk Rating (1-25) | Risk score | Analysis Of Present Controls | Control Recommendation | Treatment decision | Justification | Risk Treatment Owner | Implementation Due Date | Implementation Status | Date Implemented
1 | Fraudsters fit skimming devices and false keypads to ATMs to obtain card and PIN information. | Lacking strong kiosk security, no tamper-proof card slots, ineffective surveillance of remote ATMs. | Confidentiality: Data of the cardholder stolen. Integrity: Fraud withdrawals. Availability: ATM can be put offline when being investigated. | 4 - Likely | 5 - Severe (Catastrophe) | 20 | Extreme | CCTV present in select ATMs. When the branch has high traffic, security guards are employed. The customer is cautioned with posters against tampering. | Install anti-skimming systems and card readers that can be tampered. Tamper detecting AI-based CCTV analytics. Enhance kiosk inspection. SMS/email alerts to customers and the ATM awareness messages. | Risk Mitigation (Treat) | The skimming is widespread and effective. Layered controls can plausibly be able to decrease likelihoods of 4 (Likely) to 2 (Unlikely). | ATM Operations & Security Department | 2025-10-15 | In Progress | Pending
2 | Attackers monitor ATM communication with the central switch of the bank in order to steal sensitive customer information (card details, PINs, balances). | Other ATM implementations have old or ineffective encryption (old versions of TLS/SSL, VPN misconfigurations). Absence of certificate pinning, and insecure communication protocols enforcement. | Security: Hacked cardholder information and PINs. Integrity: There is a possibility of data being manipulated during transit of transactions. Availability: Traffic attack will result in service failure. | 3 - Possible | 5 - Severe (Catastrophe) | 15 | High | Most ATMs have VPN tunnels. Certain old ATMs still send half data on less secure encryptions. Only firewalls are able to monitor network traffic. | Application TLS 1.3 encryption to all ATM-to-switch traffic. Implement end to end card/PIN encryption. Use certificate pinning in order to avoid spoofed certificates. Periodically test encryption standards in use in ATM fleet. | Risk Mitigation (Treat) | It is possible to have Man-in-the-Middle attack in case encryption is poor. With an upgrade to strong TLS, this risk is removed in more than 90 percent. | Network Security & Infrastructure | 2025-10-31 | Planned | Pending
3 | The hackers take advantage of the new or previously unknown vulnerabilities in the ATM operating systems or supporting software, before the patches are created and implemented. | Weak patch management process- patches are not applied or delayed. High number of ATM fleet, most with legacy or non-supported operating systems. Weak threat intelligence integration to attack in advance. | Confidentiality: Hackers will have access to sensitive ATM or transaction information. Integrity: Withdrawals that are not authorized, distortion of balances or even fraud. Availability: ATM services can be crashed by exploits which results in downtime. | 4 - Likely | 4 - Major | 16 | High | Patching currently handled manually and occasionally delayed. Antivirus solutions in place but not effective against zero-day threats. Threat intelligence monitoring is weak. | Implement automated patch management systems with centralized enforcement. Subscribe to global threat intelligence feeds to detect zero-day exploits early. Deploy Endpoint Detection & Response (EDR) solutions to catch unusual activity. Maintain incident response playbooks for rapid zero-day exploitation response | Risk Mitigation (Treat) | Zero-day exploits are inevitable, but reducing patch delays + adding EDR significantly lowers exposure window and impact. | Cybersecurity & Infra | 2025-09-30 | Planned | Pending
4 | The failure of the single Internet Service Provider (ISP) linking ATMs to the central systems of the bank leads to the unavailability of ATM services. | Relying on a single ISP. None of the automatic failover systems. Absence of redundant communication channels (e.g.,4G/Satellite backup). | Availability: ATMs that fail to process the transactions during outage. Integrity: No direct effects. Confidentiality: There is no direct effect. | 3 - Possible | 4 - Major | 12 | High | Bank uses a single ISP across ATM network. Manual escalation to ISP in case of outage. No secondary backup line. | Deploy multi-ISP strategy with automatic failover. Configure VPN redundancy across ISPs. Add 4G/Satellite fallback for rural or critical ATMs. Conduct regular failover drills to ensure readiness. | Risk Mitigation (Treat) | Redundant ISPs and backup connections ensure availability; this is a cost-effective, industry-standard resilience measure. | IT Infrastructure | 2025-10-31 | Planned | Pending
5 | Attackers bombard the ATM network communication channels with high traffic, blocking systems and disrupting the service. | Absence of Intrusion Detection/ Prevention Systems (IDS/IPS). The firewalls only have basic access rules and not traffic anomaly detection. None of the ISP or third-party dedicated DDoS protection service. | Absence of Intrusion Detection/ Prevention Systems (IDS/IPS). The firewalls only have basic access rules and not traffic anomaly detection. None of the ISP or third-party dedicated DDoS protection service.. | 3 - Possible | 5 - Severe (Catastrophe) | 15 | High | Firewalls are in place but limited to static filtering. Monitoring is reactive rather than proactive. ISP does not provide advanced DDoS mitigation currently. | Deploy IDS/IPS solutions to detect and mitigate abnormal traffic. Partner with ISP for cloud-based DDoS mitigation services. Establish traffic rate limiting and geo-blocking for suspicious IPs. Create an incident response playbook for handling large-scale DDoS attacks. | Risk Mitigation (Treat) | A layered defense combining ISP support, IDS/IPS, and incident response reduces the impact of volumetric attacks significantly. | SOC | 2025-10-31 | Planned | Pending
6 | Without being detected in time, attackers/insiders make unauthorized withdrawals using stolen, cloned, or compromised credentials/cards. | Absence of real time monitoring of abnormal withdrawal activity. Inconclusive association of ATM transactions and fraud detection system. Daily batch, as opposed to real-time, alerts. | Integrity: Fraud takes away transactional trust. Confidentiality: Loss of customer account security. Availability: ATM can be disabled following fraud cases, which impacts customer service. | 4 - Likely | 5 - Severe (Catastrophe) | 20 | Extreme | Daily reconciliation reports generated. Customers sometimes receive SMS/email alerts for transactions. Fraud team manually investigates flagged cases. | Implement real-time fraud detection using AI/ML algorithms. Deploy Security Information & Event Management (SIEM) for ATM transaction monitoring. Enable geolocation-based anomaly detection (e.g., impossible travel scenarios). Automatic blocking of suspicious transactions until verified. | Risk Mitigation (Treat) | Real-time fraud monitoring reduces detection window from 24 hours â†’ minutes, lowering fraud impact drastically. | Fraud Risk Mgmt | 2025-10-15 | In Progress | Pending
7 | The criminals steal or destroy the whole ATM machine to have a direct access to the cash vault or make brute force attacks to the safe. | ATMs located in remote and unattended places. Poor physical anchoring (e.g. not screwed on the floor). | Availability: ATM is out of circulation until it is replaced/repaired. Integrity: The manipulation might harm transaction logs and sensors. Confidentiality: Low, unless the storage devices in the ATM are accessed. | 2 - Unlikely | 4 - Major | 8 | Medium | ATMs bolted to floors. Basic locks and safes installed. Security guards present at some high-traffic branches, but not rural ATMs. | Reinforce ATMs with stronger vaults and anchoring systems. Install tamper alarms and GPS trackers in ATM safes. Use CCTV monitoring linked to central security hub. Collaborate with local law enforcement for rapid response in high-risk areas. | Risk Mitigation (Treat) + Transfer (Share/Transfer) | While rare, theft of an ATM is high-impact; preventive measures reduce exposure and increase deterrence. | Physical Security | 2025-12-31 | Planned | Pending
8 | Local or regional blackouts cause ATM services to go off, particularly where there are no local or regional power blacks. | Many ATMs do not have the Uninterruptible Power Supply (UPS). No backup of generators to branch/ATM kiosks. | Availability: Atms become offline and the customers are denied the access to cash. Integrity: The transaction logs can be partial when the ATM breaks down in between transactions. Confidentiality: The confidentiality is not directly affected. | 3 - Possible | 3 - Moderate | 9 | Medium | Some ATMs in metro areas have UPS backup. Rural ATMs often lack any backup systems. Power outage contingency not uniformly applied across all sites. | Install UPS systems at all standalone ATMs. Ensure branch-based ATMs connect to branch generators. Explore solar-powered ATM kiosks in rural areas. Update BCP/DR plans to prioritize ATM uptime. | Risk Mitigation (Treat) | Outages are common and predictable; preventive backup solutions ensure ATM availability and improve customer satisfaction. | Facilities/BCP | 2025-11-30 | Planned | Pending
9 | Card trapping: the scammers install machines (or employ methods) that hold the ATM card of a customer within the reader (card capture). The attacker then obtains the trapped card later or applies distraction / social engineering techniques to obtain the PIN of the customer and conduct fraudulent transactions. | The design of ATM card reader enables easy storage of thin traps/ devices. None of the useful sensors to detect foreign objects or card retention. Untrained employees and clients who do not know how cards trap. Lack of real time alerts in case of retained or jammed card. | Confidentiality: Card information and PIN can be revealed in case of coercion and social-engineering of customer. Integrity: Fraudulent transactions can be carried out using card after retrieving it. Availability: ATM is unavailable to the customer temporarily; the machine can be put offline to be checked/repaired. | 4 - Likely | 3 - Moderate | 12 | High | Some ATMs have basic sensors that detect card jams, but many older readers do not. CCTV covers many kiosks, but video is not always monitored in real time. Customer awareness limited to occasional posters; no proactive in-ATM messaging about card trapping. Branch/Site maintenance teams respond to reported jams, but response time varies and there’s no automated escalation. | Install anti-trap / anti-skimming card readers that resist insertion of foreign devices and auto-eject suspicious objects. Add card presence / obstruction sensors that trigger immediate alarm and lock the card reader to prevent retrieval by attackers. Configure automatic alerts to the central security/SOC and branch operations when a card is retained or jammed (SMS/email/console alerts). Enable remote disable/lockdown for an ATM when tampering is detected, preventing further transactions until safe. | Risk Mitigation (Treat) | Card trapping is relatively easy to carry out and can be performed at scale in poorly monitored ATMs. Technical upgrades (anti-trap readers + sensors + automated alerts) and operational changes (awareness + faster response) materially reduce both likelihood and impact. | ATM Ops | 2025-12-31 | Planned | Pending
10 | Fraud Attackers can use vulnerabilities in the integration between the mobile bank application and ATM services (e.g., cardless cash, mobile-to-ATM withdrawal APIs, or OTP synchronization) to carry out fraudulent transactions, replay attacks, or session hijacking. APIs that are weak or improperly designed, misuse of session, or lack of proper validation enable attackers to induce or authorize ATM transactions over the Internet. | Mobile-to-ATM APIs involve poor authentication or ineffective session management. The mobile application and ATM backends do not have strong mutual authentication (no mTLS or token binding). Predictable OTPs / transaction tokens that can be reused and weak expiration processing. Poor validation on the input and rate limiting of the API endpoints. Defective logging and monitoring of ATM transactions triggered by a mobile device. | Confidentiality: Attackers may give the mobile session tokens, OTPs or user credentials. Integrity: Attackers might operate or approve fraudulent withdrawals without a card or manipulate the parameters of transaction. Availability: API abuse would potentially lead to service disruption or block out users. | 3 - Possible | 4 - Major | 12 | High | Mobile app uses standard authentication (username/password + OTP) but not all APIs enforce strict token lifetimes. Some endpoints rate-limit requests, but throttling rules are inconsistent. No mutual TLS (mTLS) or token binding for mobile-to-backend communication in all flows. Basic logging exists, but correlation between mobile app events and ATM transactions is limited. Cardless withdrawal feature exists but with limited additional verification (sometimes OTP only). | Enforce strong API authentication & mutual authentication: implement mTLS or OAuth2 with short-lived tokens and token binding to the device. Strengthen transaction authorization: require multi-factor confirmation for cardless withdrawals (e.g., device biometric + one-time code tied to device session). Harden OTP usage: use non-replayable tokens, one-time-use transaction tokens with strict expiry (e.g., 90 seconds) and single-use enforcement. Input validation & server-side checks: validate all client parameters server-side to prevent parameter tampering or replay. | Risk Mitigation (Treat) | Mobile banking features are convenient but expand attack surface. Strengthening API auth, token handling, and transaction validation materially reduces the chance of remote fraud and replay attacks. | Mobile Banking Team | 2025-10-31 | Planned | Pending
11 | Thieves obtain physical access to an ATM, attach rogue tools (e.g., by USB, serial, or network) and install malware or give orders to dispel currency (jackpotting). | Physical ports (USB, network) that are exposed / accessible (behind or inside the ATM). Lax port security (port not disabled). There is no secure boot and firmware integrity checking in ATMs. Weak physical security measures on access doors. | Availability: The ATMs lost all the money, and had to shut down. Integrity: Rule violations are done through unauthorized commands. Confidentiality: Malware is also capable of extracting customer information. | 3 - Possible | 5 - Severe (Catastrophe) | 15 | High | Some ATMs have plastic port covers, but they can be easily bypassed. Antivirus installed but ineffective against custom malware. Security guards may deter casual attackers but cannot prevent targeted jackpotting. | Physically lock or disable all unused ports (USB/network/serial). Implement secure boot and digitally signed firmware to prevent unauthorized code execution. Install intrusion detection alarms when ATM access panels are opened. Regularly audit ATM hardware for unauthorized devices. Train security staff to recognize jackpotting attempts. Deploy EDR solutions to detect unusual processes on ATM systems. | Risk Mitigation (Treat) | Jackpotting is high-likelihood and high-impact. Layered defense (physical + software + monitoring) drastically lowers success probability. | ATM Ops + IT Security | 2025-09-30 | In Progress | Pending
12 | ATM that are on the ground or in basements are destroyed by heavy rains or floods and become ineffective, destroying hardware and cash stores. | Automated Teller Machines located in flood flood-prone places. There are no waterproofing, or raising the critical ATM parts. Absence of disaster recovery planning in the case of natural disasters in prone areas. | Availability: The ATM is out of service because of water or power leakage. Integrity: Data in transactions might be corrupt in case of system failure during operation. Confidentiality: Low, absent when the attackers retrieve physical storage mediums following damage during floods. | 2 - Unlikely | 4 - Major | 8 | Medium | Some ATMs placed on elevated platforms in urban areas. Insurance policies cover ATM hardware damage in some contracts. No consistent preventive measures across all flood-prone regions. | Relocate ATMs in high-risk flood zones to elevated or safe areas. Install waterproofing and drainage systems for kiosks. Elevate power supplies and network equipment above ground level. Include disaster recovery (DR) and continuity planning for ATMs in vulnerable regions. Conduct seasonal risk assessments before monsoon periods. Ensure insurance coverage is up-to-date for natural disasters. | Risk Mitigation (Treat) + Transfer (Share/Transfer) | While natural disasters cannot be prevented, physical relocation, waterproofing, and DR planning significantly reduce downtime and financial loss. | Facilities/BCP | 2025-12-31 | Planned | Pending
13 | When ATM cash replenishment is done, internal employees or vendor personnel are going to underreport the amount loaded and either pocket the difference or conspire to false records. | No two person rule (no dual-control process). Late reconciliation of the records and cash dispensed in Core Banking System (CBS). Poor audit and control of the cash loading activities. Low CCTV coverage in the replenishment. | Integrity: Accounting records being altered; ATM balances altered. Availability: ATM can lose money sooner through underloading. Confidentiality: Not directly affected. | 3 - Possible | 4 - Major | 12 | High | Staff submit replenishment slips and reconciliation reports. Cash Ops team reviews balances at end of day. CCTV footage exists, but not consistently reviewed. Vendor staff rotation exists, but monitoring remains weak. | Enforce dual-control process (two authorized individuals required for cash loading). Conduct real-time reconciliation of cash replenishment with CBS records. Mandate CCTV recording of replenishment operations with central review. Perform surprise audits of cash loading activities. Deploy smart cash cassettes with IoT sensors to record exact cash movements. Include penalty clauses in vendor contracts for discrepancies. | Risk Mitigation (Treat) | MonitoriFraudulent cash loading directly affects customer trust. Dual control + IoT monitoring and surprise audits drastically reduce likelihood.ng reduces insider fraud. | Cash Ops & Audit | 2025-10-31 | In Progress | Pending
14 | Fraud or technical problems at ATM go unnoticed or delayed since there is still a lot of manual fraud detection, which can be performed daily rather than in real-time | No automatic fraud detector system connected with ATM switch. Daily batch reconciliation implies that fraud can remain unnoticed between 24-48 hours. There are non-centralized logs; there is no correlation between ATM events done across channels. Lack of enough human resource to review all the alerts and transactions manually. | Integrity: The fraudulent transactions might not be identified early. Availability: ATMs can be disconnected to be investigated once fraud increases. Confidentiality: Customer information may be stolen and not monitored. | 4 - Likely | 4 - Major | 16 | High | Manual reconciliation performed daily by Cash Ops. Basic alerts for ATM downtime or suspicious withdrawal spikes. Some fraud detection rules exist but not AI-driven and not cross-channel. | Deploy real-time fraud monitoring system with AI/ML analytics. Integrate ATM switch logs, CBS logs, and mobile/online banking into SIEM. Create dynamic fraud detection rules (velocity checks, impossible travel, multi-channel fraud). Train fraud teams on forensic analysis and build automated workflows for rapid case escalation. Run fraud red-teaming simulations to test detection capability. | Risk Mitigation (Treat) | Manual fraud detection introduces significant delays. Automation reduces likelihood of prolonged undetected fraud and ensures early remediation. | Fraud Risk & SOC | 2025-10-31 | In Progress | Pending